Mountain Friends Camp 5-Year Plan (2009-2014)

| goal/year | 1 (June 2010) | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Achievements | -15-25 campers -1 week -Pilot Program -Camping/Hiking -Quaker Process + values -some kind of program | -15-25 campers -2 weeks -Decide Affiliation -Final list of scouted sites | -20-35 campers -4 weeks -2 week session -possible | -25-50 campers -6 weeks | -30-60 campers -2 months -Know who we are -Year round community -Institutional relationship -Clear identity-organization -Counselor stability -Know camper makeup and market accordingly |
| Actions/ Logistics | -Insurance -Safety plan -Scouting locations -SYF committee will make decisions -Plan camp well Marketing/outreach -Yearly timeline -Budget-Research: grants/donations/law -Open a bank account -Line item in IMYM budget to collect donations | -Insurance -Safety plan -Feedback => (all years) -Finalize test locations -Budget/how to pay staff/look for grants -Ask Monthly Meetings for approval | -Insurance -Safety plan -Feedback => (all years) -Solidify counselor training program /system | -Insurance -Safety plan -Feedback => (all years) | -Insurance -Safety plan -Working counselor process -Training Programing -Marketing and Outreach -Built in feedback and evaluation |
| Resources | -Private volunteered land or public land -Volunteer staff -Paying campers (all years) Donations/sponsorship -Transportation, supplies -FGC resources (?) | -Temporary location -Paid staff? -Paying campers -Increasing sponsorship | -Test location 1 -Paid staff -Paying campers -Increasing sponsorship | -Test location 2 -Paid staff -Paying campers -Increasing sponsorship | -Permanent location (long term arrangement/own land) -Paid staff -Paying campers/family -Financial sustainability -Financial responsibility |

| Actual Progress-What we did Pilot Program: -4 campers (paid $150) -3 junior counselors, 4 adult staff (2 YAF, 2 OAF/FAP(including one Kitchen ogre) all volunteers) -2 half-day early days seminars staff training, written safety plan and emergency procedures, discussion during counselor training -written “call to MFC” , registration form, release waiver -Camping on private land -Quaker process/practice, plork projects and simple/sustainable lifestyle -SYF committee transformed into ad hoc IMYM committee, with 5 fading to 2 active YAF members (Ana-convener plus David W) and 4-6 adults -IMYM insurance-extended event medical coverage for our week-no liability/child care insurance. liability release waiver -Not enough outreach-email to our list, monthly meeting clerks, facebook, 2 campers signed up before IMYM, 3 during gathering, most hadn't heard about/didn't want to go until during IMYM Quaker EarthCare Witness Mini-grant-2009-10, $250 Did not do: 15 campers, separate bank account, scout potential permanent locations, write yearly time-line, use FGC resources | Actual Progress-What we did year 2: -10 campers ($150 each) (all 4 returned from pilot program plus 6 new campers) -6 adult staff (2 YAF(including 1 acting director) 4 OAF/FAP (including 1 Kitchen) all volunteers) -Phone conversations with committee, potential and returning staff, emails and 1 staff meal at IMYM for planning -Camping on private land -Quaker process/practice, plork-sustainability projects and lifestyle -Scouting potential long term locations! -Ad hoc committee-Ana convener(/”acting director”) plus Ariel, Val I, Eileen, Chris, Claire, Brenda and Pat, some input from Jr Counselors after camp, Eric and Ian before and after camp -IMYM insurance, written registration materials (plus staff questions and health info), safety plan -Outreach and Marketing- 6 weeks visiting monthly and regional meetings to talk with Friends/families about camp. Visited returning and new campers, distributed brochures and registration forms, showed pictures from pilot program, raised over $2000 in donations from Meetings and individuals, 2 newsletters, 3 “on the quaker road” articles, 1 tri-fold brochure, health form and additional questions for counselors, Did not do: 15 campers, 2 weeks, bank account, make “final list” of potential permanent sites In process, Fall 2011: decide relationship with IMYM, ask Monthly Meetings for approval, create system to pay staff, write yearly time-line, apply for grants, consider long term locations | Revise plan for years 3-5... length of sessions -2-6 weeks with 2-7 days of staff training increase camper fee ($300-500/week), sliding scale? Increase scholarships. Ask Monthly Meetings to minute support for all Young Friend who need financial aid. -pay staff, director(s) to work off season and seasonal staff ( program/counselors, kitchen staff.) Stipends to a pt salary? -long term location-written agreement for use or ideally our own land! -clearly defined relationship with IMYM, independent or linked finances/legal standing? -standing committee with written description and structure, -incorporation, 501c3 status (?) |
| --- | --- | --- |